## Reports
GARMCO e-Tendering System
Enhancement and Incident Log Sheet
Current Status
| Cancelled | 0
| Closed | 5
| For Verification | 0
| In-progress | 2
| Open | 9
| TOTAL | 16
Item No. | Type | Application | Description | Reported By | Reported Date | Status | Actioned By | Date Fixed | Remarks
1 | Enhancement | B2B Admin | Ability to partially process RFQ | Sayed | 2013-06-17 | Open
2 | Enhancement | B2B Admin | Invite other suppliers while the RFQ is still open | Sayed | 2013-06-17 | Closed
3 | Enhancement | B2B Admin | Ability to cancel or close RFQ any time with justification | Sayed | 2013-06-17 | In-progress |  |  | To allow buyers to cancel, close or set the status to manually process. The latter will be implemented in-case the RFQ has been processed already in JDE
4 | Incident | B2B Admin | The current reminder doesn't work accordingly. If there are three suppliers to be reminded, all three suppliers get three emails which contain even the reminder email from other suppliers | Sayed | 2013-06-17 | Open
5 | Enhancement | B2B Admin | To have a communication facility between buyer and suppliers | Sayed | 2013-06-17 | In-progress
6 | Enhancement | B2B Admin | To send acknowledgement letter for those who have participated and didn't win | Sayed | 2013-06-17 | Closed |  |  | An acknowledgement letter will be sent to all suppliers who were not chosen in the bidding, and this will only happen once the related PO has been approved completely. The email will contain the order lines wherein the supplier was not chosen
7 | Enhancement | B2B Admin | The Buyer Inquiry page needs to be organized | Sayed | 2013-06-17 | Closed
8 | Enhancement | B2B Admin | Improve layout and eliminate duplicate commands | Sayed | 2013-06-17 | Closed |  |  | Inquiry pages (e.g. Published RFQ, Buye Inquiry and even in the e-Tendering System) will be re-designed similar to Order Inquiry page from GAP System
9 | Incident | e-Tendering | The temporary password of the secondary contact person is the same with the primary during registration | Sayed | 2013-06-17 | Open
10 | Incident | e-Tendering | To allow supplier to delete his/her quote | Sayed | 2013-06-17 | Open
11 | Enhancement | e-Tendering | To include the name of the buyer in the email notification during publishing of an RFQ | Sayed | 2013-06-17 | Open
12 | Enhancement | e-Tendering | Some extra fields msut be added to Supplier's Quote Entry page - Unit Price - Delivery Terms - Payment Terms - Remarks - Supplier Reference No. | Sayed | 2013-06-17 | Open
13 | Enhancement | B2B Admin | To have a facility to resend the activatio link and password to supplier | Sayed |  | Closed
14 | Enhancement | B2B Admin | To view previous suppliers on a given RFQ | Tender Committee | 2013-07-02 | Open
15 | Enhancement | B2B Admin | To set the priority prior to publishing the RFQ from JDE so an email with an URGENT will be sent | Sayed | 2013-07-11 | Open
16 | Enhancement | e-Tendering | To attach the company profile during the registration | Sayed | 2013-10-23 | Open
Please insert new rows above this line

## Reference (hidden)
Incident
Enhancement
Cancelled
Closed
For Verification
In-progress
Open
e-Tendering
B2B Admin